## Mielstones
Date | Delivery
May 20 th | Kick off
June 4 th | Start of work
June 13 th | Different models created
June 20 th | XAI and UQ implemented
June 27 th | First version of modeling tool
July 4 th | Prototype for GUI
July 18 th | Production ready GUI including labeling tool
August 1st | Improved models
September 5 th | Results transferred to demonstrator (design and components of demonstrator will be my task)

## Time Schedule
|  | 2025-06-04 | 2025-06-13 | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29 | 2025-09-05 | 2025-09-12 | 2025-09-19 | 2025-09-26 | 2025-10-03
Baseline Models | Modeling | bar: 2025-06-04 to 2025-06-13
Testing + documentation | bar: 2025-06-20 to 2025-06-27
XAI and Uncertainty Quantification | Selection of methods | bar: 2025-06-04
Implementation | bar: 2025-06-13 to 2025-06-20
Testing + documentation | bar: 2025-06-20 to 2025-06-27
Labeling tool | Requirements | bar: 2025-06-13 to 2025-06-20
Implementation | bar: 2025-06-20 to 2025-06-27
Testing + documentation | bar: 2025-06-20 to 2025-07-04
GUI | Requirements | bar: 2025-06-13 to 2025-06-27
Implementation | bar: 2025-06-27 to 2025-07-04
Integration of labeling tool | bar: 2025-07-04 to 2025-07-18
Model Improvement | Definition of process | bar: 2025-06-27 to 2025-07-18
Conduction of tests | bar: 2025-07-18 to 2025-08-01
Demonstrator | Definition of setting | bar: 2025-07-04 to 2025-07-18
Preparation of construction | bar: 2025-07-18 to 2025-08-01
Construction and commissioning | bar: 2025-08-01 to 2025-09-05
Documentation | bar: 2025-08-01 to 2025-09-26
Sagar
Julius